## Cover
Project Challenge 2
Team 1
| Team Member : | 1 | Ye Pyie ->Aung Min Khant
|  | 2 | Nan Nay Chi Linn -> Zayar
|  | 3 | Nyi Myo Set
|  | 4 | Moh Moh Khin
|  |  |  | Create Date | 2022-05-17
|  |  |  | Update Date | 2022-06-17

## Customer Requirement
Customer Requirement (要件定義) | စာအုပ်ဆိုင် Book Store |  |  |  | Create Date | 2022-05-17
[5 empty] | Update Date | 2022-06-17
Customer Requirement
| 1 | Onine Book Shoping
|  | 1-1 | Admin Page (Login)
|  |  | 1-1-1 | Admin Page Inculde
|  |  | a ) | Login/Out
|  |  | b ) | Dashboard (Total View,Order & Sale,...)
|  |  | c ) | Book Info
- Add Item (Book=>Image,name,price,preview,category)
- BookList /Update/Delete
|  |  | d ) | Author Info
- Author List
- Author Add/Update/Delete
|  |  | e ) | Shop Info
- Add/Update/Delete
|  |  | f ) | Community
- Review & Rating(View)
- View From Contact Us
|  |  | g ) | Order Info
- Today Order
- Order Detail Table (userinfo)
|  |  | h ) | User Info
- view
|  |  | i) | Admin Setting
- Category Add/Update/Delete
- Logo Change
- favicon Change
- Slider Change
- Welcome Text
- Website info (phone,address,email,...)
- Guide Change
- Service Change
- PP Change
- FAQ Add/Update
- Delivery Control
|  | 2-1 | Customer Home Page
|  |  | 2-1-1 | Customer Page Inculde
|  |  | a ) | Login/Sign Up
|  |  | b ) | User Profile
|  |  | c ) | Order History
|  |  | d ) | Add To Cart/Show Cart/CheckOut
|  |  | e ) | Show Book View
|  |  | f ) | Review & Rating
|  |  | h ) | View By Category
|  |  | I ) | Search (Book Name)
|  |  | j ) | Author Profile (Name,photo,count of book,Biography)
|  |  | k ) | Shop List
|  |  | l ) | Guide of website
|  |  | m) | FAQ,Contact Us(From),Service,PrivacyPolicy

## Schedule
Schedule (進捗） |  | စာအုပ်ဆိုင် Book Store | [8 empty] | Create Date | 2021-05-17
[11 empty] | Update Date | 2022-06-17
No | Sub | Task | Assign | Est Start | Est End | Duration Day | Act Start | Act End | Act Duration | Work Done
1 |  | Schedule（進捗） | ALL | 2022-05-17 | 2022-06-03 | 17 | 2022-05-17 | 2022-06-17 | 31 | 100%
2 |  | Project Flow（流れ） | NCL/MMK | 2022-05-17 | 2022-05-20 | 3 | 2022-05-18 | 2022-05-18 | 0 | 100%
3 |  | Screen Design（画面設計） | ALL | 2022-05-17 | 2022-05-24 | 7 | 2022-05-17 | 2022-05-23 | 6 | 100%
| 1 | Home Page (User) | Ye Pyie | 2022-05-17 | 2022-05-19 | 2 | 2022-05-17 | 2022-05-19 | 2 | 100%
| 2 | Category Page | Ye Pyie | 2022-05-17 | 2022-05-18 | 1 | 2022-05-17 | 2022-05-18 | 1 | 100%
| 3 | Shop List Page | NMS | 2022-05-17 | 2022-05-18 | 1 | 2022-05-17 | 2022-05-18 | 1 | 100%
| 4 | Author Page | MMK | 2022-05-17 | 2022-05-18 | 1 | 2022-05-17 | 2022-05-18 | 1 | 100%
| 5 | Login | NCL | 2022-05-17 | 2022-05-18 | 1 | 2022-05-17 | 2022-05-18 | 1 | 100%
| 6 | SignUp | NCL | 2022-05-17 | 2022-05-18 | 1 | 2022-05-17 | 2022-05-18 | 1 | 100%
| 7 | Add to Cart Page | NMS | 2022-05-18 | 2022-05-19 | 1 | 2022-05-18 | 2022-05-19 | 1 | 100%
| 8 | View Page | NMS | 2022-05-18 | 2022-05-19 | 1 | 2022-05-18 | 2022-05-19 | 1 | 100%
| 9 | Search | Ye Pyie | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 10 | Contact Page | NCL | 2022-05-18 | 2022-05-19 | 1 | 2022-05-18 | 2022-05-19 | 1 | 100%
| 11 | FAQ | NCL | 2022-05-18 | 2022-05-19 | 1 | 2022-05-18 | 2022-05-19 | 1 | 100%
| 12 | Privacypolicy | Ye Pyie | 2022-05-22 | 2022-05-23 | 1 | 2022-05-22 | 2022-05-23 | 1 | 100%
| 13 | Guide | Ye Pyie | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 14 | Service | Ye Pyie | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 15 | User Profile | Ye Pyie | 2022-05-22 | 2022-05-23 | 1 | 2022-05-22 | 2022-05-23 | 1 | 100%
| 16 | Order History | Ye Pyie | 2022-05-21 | 2022-05-22 | 1 | 2022-05-21 | 2022-05-22 | 1 | 100%
| 17 | Voucher | Ye Pyie | 2022-05-21 | 2022-05-22 | 1 | 2022-05-21 | 2022-05-22 | 1 | 100%
| 18 | Login(Admin) | NCL | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 19 | Admin Daskboard | MMK | 2022-05-18 | 2022-05-19 | 1 | 2022-05-18 | 2022-05-19 | 1 | 100%
| 20 | Book List | NCL | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 21 | Edit Book | NCL | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 22 | Add Book | NCL | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 23 | Author List | MMK | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 24 | Add Author | MMK | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 25 | Edit Author | MMK | 2022-05-19 | 2022-05-20 | 1 | 2022-05-18 | 2022-05-19 | 1 | 100%
| 26 | Shop List Page | MMK | 2022-05-21 | 2022-05-22 | 1 | 2022-05-21 | 2022-05-22 | 1 | 100%
| 27 | Add Shop | MMK | 2022-05-21 | 2022-05-22 | 1 | 2022-05-21 | 2022-05-22 | 1 | 100%
| 28 | Edit Shop | MMK | 2022-05-21 | 2022-05-22 | 1 | 2022-05-21 | 2022-05-22 | 1 | 100%
| 29 | User Info Page | MMK | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 30 | Order Info Page | NCL | 2022-05-18 | 2022-05-19 | 1 | 2022-05-18 | 2022-05-19 | 1 | 100%
| 31 | Community Page | MMK | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 32 | Admin Setting(App Master) | NMS | 2022-05-19 | 2022-05-20 | 1 | 2022-05-18 | 2022-05-19 | 1 | 100%
| 33 | Admin Setting(Site Master) | NMS | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 34 | Login Master(Add Admin) | NMS | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 35 | Login Master(Admin List) | NMS | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
| 36 | Delivery List | NMS | 2022-05-21 | 2022-05-22 | 1 | 2022-05-21 | 2022-05-22 | 1 | 100%
| 37 | Edit Delivery | NMS | 2022-05-21 | 2022-05-22 | 1 | 2022-05-21 | 2022-05-22 | 1 | 100%
| 38 | Add Delivery | NMS | 2022-05-21 | 2022-05-22 | 1 | 2022-05-21 | 2022-05-22 | 1 | 100%
| 39 | service | MMK | 2022-05-22 | 2022-05-23 | 1 | 2022-05-22 | 2022-05-23 | 1 | 100%
| 40 | Add service | MMK | 2022-05-22 | 2022-05-23 | 1 | 2022-05-22 | 2022-05-23 | 1 | 100%
| 41 | Edit service | MMK | 2022-05-22 | 2022-05-23 | 1 | 2022-05-22 | 2022-05-23 | 1 | 100%
| 42 | Privacypolicy | NCL | 2022-05-22 | 2022-05-23 | 1 | 2022-05-22 | 2022-05-23 | 1 | 100%
| 43 | FAQ | NCL | 2022-05-20 | 2022-05-21 | 1 | 2022-05-20 | 2022-05-21 | 1 | 100%
| 44 | Add Category | NMS | 2022-05-22 | 2022-05-23 | 1 | 2022-05-22 | 2022-05-23 | 1 | 100%
| 45 | Add Guide | NMS | 2022-05-22 | 2022-05-23 | 1 | 2022-05-22 | 2022-05-23 | 1 | 100%
| 46 | Edit Guide | NMS | 2022-05-22 | 2022-05-23 | 1 | 2022-05-22 | 2022-05-23 | 1 | 100%
| 27 | Create Admin | NMS | 2022-05-19 | 2022-05-20 | 1 | 2022-05-19 | 2022-05-20 | 1 | 100%
4 |  | Database（DB設計書） | NCL | 2022-05-21 | 2022-05-24 | 3 | 2022-05-21 | 2022-05-23 | 2 | 100%
5 |  | Development（開発） | ALL | 2022-05-24 | 2022-06-03 | 10 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 1 | Home Page (User) | ZY | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 2 | Category Page | AMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 3 | Shop List Page | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-27 | 2022-06-17 | 21 | 100%
| 4 | Author Page | ZY | 2022-05-24 | 2022-05-29 | 5 | 2022-05-27 | 2022-06-17 | 21 | 100%
| 5 | Login | AMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-26 | 2022-06-17 | 22 | 100%
| 6 | SignUp | AMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-26 | 2022-06-17 | 22 | 100%
| 7 | Add to Cart Page | AMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-28 | 2022-06-17 | 20 | 100%
| 8 | View Page | AMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 9 | Search | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-25 | 2022-06-17 | 23 | 100%
| 10 | Contact Page | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 11 | FAQ | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 12 | Privacypolicy | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 13 | Guide | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 14 | Service | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-25 | 2022-06-17 | 23 | 100%
| 15 | User Profile | ZY | 2022-05-24 | 2022-05-29 | 5 | 2022-05-27 | 2022-06-17 | 21 | 100%
| 16 | Order History | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-27 | 2022-06-17 | 21 | 100%
| 17 | Voucher | AMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-28 | 2022-06-17 | 20 | 100%
| 18 | Login(Admin) | MMK,NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 19 | Admin Daskboard | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 20 | Book List | NMS,MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-28 | 2022-06-17 | 20 | 100%
| 21 | Edit Book | NMS,MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-28 | 2022-06-17 | 20 | 100%
| 22 | Add Book | NMS,MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-28 | 2022-06-17 | 20 | 100%
| 23 | Author List | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-25 | 2022-06-17 | 23 | 100%
| 24 | Add Author | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-25 | 2022-06-17 | 23 | 100%
| 25 | Edit Author | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-25 | 2022-06-17 | 23 | 100%
| 26 | Shop List Page | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-25 | 2022-06-17 | 23 | 100%
| 27 | Add Shop | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-25 | 2022-06-17 | 23 | 100%
| 28 | Edit Shop | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-25 | 2022-06-17 | 23 | 100%
| 29 | User Info Page | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-27 | 2022-06-17 | 21 | 100%
| 30 | Order Info Page | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-27 | 2022-06-17 | 21 | 100%
| 31 | Community Page | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-27 | 2022-06-17 | 21 | 100%
| 32 | Admin Setting(App Master) | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 33 | Admin Setting(Site Master) | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-27 | 2022-06-17 | 21 | 100%
| 34 | Login Master(Add Admin) | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-27 | 2022-06-17 | 21 | 100%
| 35 | Login Master(Admin List) | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-27 | 2022-06-17 | 21 | 100%
| 36 | Delivery List | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 37 | Edit Delivery | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-28 | 2022-06-17 | 20 | 100%
| 38 | Add Delivery | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-28 | 2022-06-17 | 20 | 100%
| 39 | Service List | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 40 | Add service | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 41 | Edit service | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 42 | Privacypolicy | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 43 | FAQ | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 44 | Add Guide | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 45 | Edit Guide | NMS | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 46 | Add Category | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
| 47 | Edit Category | MMK | 2022-05-24 | 2022-05-29 | 5 | 2022-05-24 | 2022-06-17 | 24 | 100%
6 |  | Unit Test（単体試験） |  |  |  | 0 |  |  | 0
7 |  | Integration Test（結合試験） |  |  |  | 0 |  |  | 0
323
[5 empty] | Month | 10.7667

## Screen Flow
Screen Flow (画面遷移） |  | စာအုပ်ဆိုင် Book Store | [5 empty] | Create Date | 2022-05-17
[8 empty] | Update Date | 2022-06-17
Explanation of Project
プロジャックの説明
(画面遷移）
| Path： | Admin |  |  |  | Path： | Customer
No
Yes
No
Yes
No
Yes
No
Yes
Admin Page
Login
valid
DashBoard
Book Info
Author Info
Shop Info
Community
Order Info
Setting
Total
-viewer
-register
-download
-order & sale
-Add item
-name
-img
-price
-preview
-stock
-category
-upload pdf
-link generate
-BookList
-Update
-Delete
Author
-list
-Add
-Update
-Delete
-Add
-Update
-Delete
-Review & Rating(view)
-View form
-Contact Us
-Today Order
-Order Detail Table (userinfo)
-user info (for view)
- Category Add/Update/Delete
LogoChange faviconChge
SliderChange
- Welcome Text
- Website info (phone,address,email,...)
- Guide Change
- Service Change
- PP Change
- FAQ Add/Update
-Create account
LogOut
Home Page
Shop
Author Profile (Name,photo,count of book,...)
Search (Category,Author,Book Name)
Category
Contact
Add to cart
view items
check out
buy?
Login
SignUp
Logout
previews
show rating
account?
give review
only view
valid
Voucher
order confirmed
Order History
UserProfile

## Screen Design
Screen Design (画面設計） |  | Project Name | [8 empty] | Create Date | 2022-05-17
[11 empty] | Update Date | 2022-06-17
Screen Name ： |  |  | Customer |  |  | Screen Name ： |  |  | Admin
| Home Page |  |  | Category Pages |  |  | Admin Login |  |  | Dashboard
[8 empty] | Book Info |  |  | Add Book
| Search Page |  |  | Author Page
Edit Book
Author Info
| BookDetails Page |  |  |  | Add to Cart Page |  |  | Add Author |  |  | Edit Author
[8 empty] | Shop Info |  |  | Add Shop
| Sign Up |  |  |  | Sign In
| Voucher |  |  |  | Order History
| View Profile |  |  |  | Shops
[8 empty] | Edit Shop |  |  | User Info
| Service |  |  |  | Guide |  |  | Order Info |  |  | Order Details
Community
| Privacy Policy |  |  | Faq
Contact us
[8 empty] | Site Master |  |  | App Master
[8 empty] | Add Category |  |  | Edit Category
[8 empty] | Add Guide |  |  | Edit Guide
[8 empty] | Add Delivery Fees |  |  | Edit Delivery Fees
[8 empty] | Add Service |  |  | Edit Service
[8 empty] | Add Privacy Policy |  |  | Edit Privacy Policy
[8 empty] | Add Faq |  |  | Edit Faq
[8 empty] | Login Master |  |  | Add Admin

## DB Design
DB Design (DB設計） |  | စာအုပ်ဆိုင် Book Store | [8 empty] | Create Date | 2022-05-22
[11 empty] | Update Date | 2022-06-17
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Admin Login
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Admins' id | Y | Y | Y | INT | 11
| 2 | admin_username | Admins' username | - | - | Y | VARCHAR | 64 |  | unique
| 3 | admin_email | Admins' email | - | - | Y | VARCHAR | 64
| 4 | admin_password | Admins' password | - | - | Y | VARCHAR | 128
| 5 | del_flg | Delete flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 6 | create_date | admins' create date | - | - | N | VARCHAR | 10
| 7 | create_by | admins' create by person | - | - | N | VARCHAR | 64
| 8 | update_date | admins' update date | - | - | Y | VARCHAR | 10
| 9 | update_by | admins' update by person | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Book
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Book_list's id | Y | Y | Y | INT | 11
| 2 | book_image | Book_list' book image | - | - | Y | VARCHAR | 256
| 3 | book_name | Book_list' book name | - | - | Y | VARCHAR | 256
| 4 | author_id | author's id | - | - | Y | INT | 11
| 5 | book_size | Book' size | - | - | Y | VARCHAR | 64
| 6 | book_established | Book' established | - | - | Y | VARCHAR | 11
| 7 | book_pages | Book' pages | - | - | Y | INT | 11
| 8 | book_description | book_description | - | - | N | VARCHAR | 256
| 9 | category_id | Book_list'category | - | - | Y | INT | 11
| 10 | book_price | Book_list' price | - | - | Y | INT | 11
| 11 | view_count | Book_view_count | - | - | Y | INT | 11
| 12 | rating | Book Rating | - | - | Y | INT | 10
| 13 | del_flg | Delete Flg | - | - | Y | INT | 11 |  | 0:Exist,1:Delete
| 14 | create_date | Book_list' create date | - | - | N | VARCHAR | 10
| 15 | create_by | Book_list' create by person | - | - | N | VARCHAR | 64
| 16 | update_date | Book_list' update date | - | - | Y | VARCHAR | 10
| 17 | update_by | Book_list' by person | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Category
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Category's ID | Y | Y | Y | INT | 11
| 2 | category_name | Category's Name | - | - | Y | VARCHAR | 256 |  | unique
| 3 | del_flg | Delete flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 4 | create_date | Book' create date | - | - | N | VARCHAR | 10
| 5 | create_by | Book' create by person | - | - | N | VARCHAR | 64
| 6 | update_date | Book' update date | - | - | Y | VARCHAR | 10
| 7 | update_by | Book' update by person | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Author
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Authors' id | Y | Y | Y | INT | 11
| 2 | author_name | Authors' name | - | - | Y | VARCHAR | 256 |  | unique
| 3 | author_image | Authors' image |  | - | Y | VARCHAR | 256
| 4 | author_bio | Authors' biography |  | - | Y | VARCHAR | 1024
| 5 | del_flg | Delete flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 6 | create_date | Authors' create date | - | - | N | VARCHAR | 10
| 7 | create_by | Authors' create by person | - | - | N | VARCHAR | 64
| 8 | update_date | Authors' update date | - | - | Y | VARCHAR | 10
| 9 | update_by | Authors' update by person | - | - | Y | VARCHAR | 64
| DB Name ： |  | Book_DB
| Table Name ： |  | Add_Author
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Authors' id | Y | Y | Y | INT | 11
| 2 | name | Authors' name | - | - | Y | VARCHAR | 256 |  | unique
| 3 | image | Authors' image |  | - | Y | VARCHAR | 256
| 4 | biography | Authors' bio |  | - | Y | VARCHAR | 256
| 5 | del_flg | Delete flg | - | - | Y | INT | 1 | - | 0:Exist,1:Delete
| 6 | create_date | Authors' create date | - | - | N | INT | 11
| 7 | create_by | Authors' create by person | - | - | N | VARCHAR
| 8 | update_date | Authors' update date | - | - | Y | timestamp
| 9 | update_by | Authors' update by person | - | - | Y | timestamp
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Shop
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Shops' id | Y | Y | Y | INT | 11
| 2 | shop_name | Shops' name | - | - | Y | VARCHAR | 256
| 3 | shop_image | Shops' image | - | - | Y | VARCHAR | 256
| 4 | shop_city | Shops' township | - | - | Y | VARCHAR | 64
| 5 | shop_address | Shops' address | - | - | Y | VARCHAR | 256
| 6 | shop_phone_no | Shops' phone_no | - | - | Y | VARCHAR | 64
| 7 | shop_website | Shops' website | - | - | Y | VARCHAR | 256
| 8 | del_flg | Delete flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 9 | create_date | shops' create date | - | - | N | VARCHAR | 10
| 10 | create_by | shops' create by person | - | - | N | VARCHAR | 64
| 11 | update_date | shops' update date | - | - | Y | VARCHAR | 10
| 12 | update_by | shops' update by person | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | User_List
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Users' id | Y | Y | Y | INT | 11
| 2 | user_name | Users' name | - | - | Y | VARCHAR | 256 |  | unique
| 3 | user_email | Users' email | - | - | Y | VARCHAR | 256
| 4 | user_password | Users' password | - | - | Y | VARCHAR | 256
| 5 | user_phone | Users' phone | - | - | Y | VARCHAR | 15
| 6 | user-address | Users' address | - | - | Y | VARCHAR | 256
| 7 | user_valid | User_valid | - | - | Y | INT | 11 |  | 0:valid,1:ban
| 8 | del_flg | Delete flg | - | - | Y | INT | 11 |  | 0:Exist,1:Delete
| 9 | create_date | Users' create date | - | - | N | VARCHAR | 10
| 10 | create_by | Users' create by person | - | - | N | VARCHAR | 64
| 11 | update_date | Users' update date | - | - | Y | VARCHAR | 10
| 12 | update_by | Users' update by person | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Orders
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Orders' id | Y | Y | Y | INT | 11
| 2 | customer_id | Orders' customer_id | - | - | Y | INT | 11
| 3 | delivery_fees_id | Order' Delivery Fees | - | - | Y | INT | 11
| 4 | total_amount | Orders' total amount | - | - | Y | INT | 11
| 5 | del_flg | Delete Flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 6 | create_date | Orders' create date | - | - | N | VARCHAR | 10
| 7 | create_by | Orders' create by person | - | - | N | VARCHAR | 64
| 8 | update_date | Orders' update date | - | - | Y | VARCHAR | 10
| 9 | update_by | Orders' update by person | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Order_details
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Orders' id | Y | Y | Y | INT | 11
| 2 | user_id | Orders' user's id | - | - | Y | INT | 11
| 3 | book_id | Orders' book_id | - | - | Y | INT | 11
| 4 | order_d_quantity | Orders' quantity | - | - | Y | INT | 11
| 5 | total_amount | Orders' total amount | - | - | Y | INT | 11
| 6 | del_flg | Delete Flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 7 | create_by_month | Orders' created month | - | - | Y | VARCHAR | 10
| 8 | create_date | Orders' create date | - | - | N | VARCHAR | 10
| 9 | create_by | Orders' create by person | - | - | N | VARCHAR | 64
| 10 | update_date | Orders' update date | - | - | Y | VARCHAR | 10
| 11 | update_by | Orders' update by person | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Contact_Form
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Contact_Form' id | Y | Y | Y | INT | 11
| 2 | contact_form_name | Contact_Form' name | - | - | Y | VARCHAR | 64
| 3 | contact_form_email | Contact_Form' email | - | - | Y | VARCHAR | 256
| 4 | contact_form_massage | Contact_Form' massage | - | - | Y | VARCHAR | 1024
| 5 | del_flg | Delete Flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 6 | create_date | Contact_Form' create date | - | - | N | VARCHAR | 10
| 7 | create_by | Contact_Form' create by | - | - | N | VARCHAR | 64
| 8 | update_date | Contact_Form' create date | - | - | Y | VARCHAR | 10
| 9 | update_by | Contact_Form' by | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | review_rating
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Customer's comment' id | Y | Y | Y | INT | 11
| 2 | customer_id | Customer's_id | - | - | Y | INT | 11
| 3 | book_id | Customer's comment' book_id | - | - | Y | INT | 11
| 4 | category_id | Book category's id | - | - | Y | INT | 11
| 5 | customer_comment | Customer's comment | - | - | Y | VARCHAR | 256
| 6 | customer_rating | View_Rating's rating | - | - | Y | INT | 11
| 7 | del_flg | Delete Flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 8 | create_date | Customer's comment' create date | - | - | N | VARCHAR | 10
| 9 | create_by | Customer's comment' create by | - | - | N | VARCHAR | 64
| 10 | update_date | Customer's comment' update date | - | - | Y | VARCHAR | 10
| 11 | update_by | Customer's comment' by | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Slider
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | Cart_items' id | Y | Y | Y | INT | 11
| 2 | slider_image1 | Slide image 1 | - | - | Y | VARCHAR | 256
| 3 | slider_image2 | Slide image 2 | - | - | Y | VARCHAR | 256
| 4 | slider_image3 | Slide image 3 | - | - | Y | VARCHAR | 256
| 5 | slider_image4 | Slide image 4 | - | - | Y | VARCHAR | 256
| 6 | del_flg | Delete Flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 7 | create_date | Cart_Lists' create date | - | - | N | VARCHAR | 10
| 8 | create_by | Cart_Lists' create by person | - | - | N | VARCHAR | 64
| 9 | update_date | Cart_Lists' update date | - | - | Y | VARCHAR | 10
| 10 | update_by | Cart_Lists' update by person | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Site_Master
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | site id | Y | Y | Y | INT | 11
| 2 | web_name | websites' name | - | - | Y | VARCHAR | 256 |  | unique
| 3 | web_logo | websites' logo | - | - | Y | VARCHAR | 256
| 4 | web_slider_text_1 | websites' text_1 | - | - | Y | VARCHAR | 256
| 5 | web_slider_text_2 | websites' text_2 | - | - | Y | VARCHAR | 256
| 6 | web_phno | websites' phone no. | - | - | Y | VARCHAR | 64
| 7 | web_email | websites' email | - | - | Y | VARCHAR | 64
| 8 | web_address | websites' shop address | - | - | Y | VARCHAR | 256
| 9 | g_map_link | googlemap_link | - | - | Y | VARCHAR | 256
| 10 | del_flg | Delete Flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 11 | create_date | webistes' create date | - | - | N | VARCHAR | 10
| 12 | create_by | webistes' create by person | - | - | N | VARCHAR | 64
| 13 | update_date | webistes' update date | - | - | Y | VARCHAR | 10
| 14 | update_by | webistes' update by person | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Guide
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | guide id | Y | Y | Y | INT | 11
| 2 | guide_text | guide text | - | - | Y | VARCHAR | 256
| 3 | guide_image | guide image | - | - | Y | VARCHAR | 256
| 4 | del_flg | Delete Flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 5 | create_date | guides' create date | - | - | N | VARCHAR | 10
| 6 | create_by | guides' create by | - | - | N | VARCHAR | 64
| 7 | update_date | guides' update date | - | - | Y | VARCHAR | 10
| 8 | update_by | guides' update by | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Faq
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | faq_id | Y | Y | Y | INT | 11
| 2 | faq_q_text | faq question text | - | - | Y | VARCHAR | 256
| 3 | faq_ans_text | faq answer text | - | - | Y | VARCHAR | 256
| 4 | del_flg | Delete Flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 5 | create_date | guides' create date | - | - | N | VARCHAR | 10
| 6 | create_by | guides' create by | - | - | N | VARCHAR | 64
| 7 | update_date | guides' update date | - | - | Y | VARCHAR | 10
| 8 | update_by | guides' update by | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | Delivey_fee
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | delivery id | Y | Y | Y | INT | 11
| 2 | delivery_city_name | delivery city name | - | - | Y | VARCHAR | 256
| 3 | delivery_fees | delivery fees | - | - | Y | INT | 11
| 4 | del_flg | Delete Flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 5 | create_date | guides' create date | - | - | N | VARCHAR | 10
| 6 | create_by | guides' create by | - | - | N | VARCHAR | 64
| 7 | update_date | guides' update date | - | - | Y | VARCHAR | 10
| 8 | update_by | guides' update by | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | privacypolicy
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | faq_id | Y | Y | Y | INT | 11
| 2 | pp_title | pp_title | - | - | Y | VARCHAR | 256
| 3 | pp_paragraph | pp_paragraph | - | - | Y | VARCHAR | 1024
| 4 | del_flg | Delete Flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 5 | create_date | guides' create date | - | - | N | VARCHAR | 10
| 6 | create_by | guides' create by | - | - | N | VARCHAR | 64
| 7 | update_date | guides' update date | - | - | Y | VARCHAR | 10
| 8 | update_by | guides' update by | - | - | Y | VARCHAR | 64
| DB Name ： |  | Paradise Book Store
| Table Name ： |  | service
| No | Field Name | Description | PK | AI | NN | Type | Length | FK | Remark
| 1 | id | service_id | Y | Y | Y | INT | 11
| 2 | service_title | service_title | - | - | Y | VARCHAR | 256
| 3 | service_paragraph | service_paragraph | - | - | Y | VARCHAR | 1024
| 4 | del_flg | Delete Flg | - | - | Y | INT | 11 | - | 0:Exist,1:Delete
| 5 | create_date | guides' create date | - | - | N | VARCHAR | 10
| 6 | create_by | guides' create by | - | - | N | VARCHAR | 64
| 7 | update_date | guides' update date | - | - | Y | VARCHAR | 10
| 8 | update_by | guides' update by | - | - | Y | VARCHAR | 64